## Weekly Status Report 1
Sample Weekly Status Report
By www.softwaretestingclass.com
Project Name: | XYZ Systems |  | SUMMARY
Project ID: | W10978 |  | Total Test Cases | 5
Application ID/Name: | XYZ Accounting |  | Executed | 2
From Report Date: | 2015-04-11 |  | Pass | 1
Report Date: | 2015-04-17 |  | Fail | 1
Complete By (Milestone): | 2015-05-08 |  | Not executed | 1
Project Manager: | Ram Ray
QA manager: | Shyam Das
FUNCTIONAL TESTING
Test Case ID | Description | Pass/Fail/Not Executed | Test Date | Responsible Developer | Responsible Tester | Comment | Additional Comment (other than QA team)
01 | Valid Login | Pass | 13-Apr-2015 | Developer 1 | Tester 1 | Login successful
02 | Login Error on invalid Login | Fail | 13-Apr-2015 | Developer 1 | Tester 2 | Incorrect error message on failure
03 | Forget Password | Not Executed | 13-Apr-2015 | Developer 3 | Tester 2 | NA

## Weekly Status Report 2
Sample Weekly Status Report
By www.softwaretestingclass.com
OPEN ISSUES | PRIORITY | ASSIGNED | TEST CASE ID | Reported DATE | STATUS | Updated Date
1 | High | QA Team | 34 | 2015-04-09 | In Progress | 2105-04-13
2 | Low | Dev Team | 98 | 2015-04-09 | Resolved | 2105-04-13
3 | Important | BA Team | 198 | 2015-04-09 | Unresolved | 2105-04-09
4 | Critical | Mangement | NA | 2015-04-09 | Closed | 2015-04-10
CLOSED ISSUES | TEST CASE ID | CLOSURE DATE |  | BUGS/DEFECT SUMMARY
1 | 87 | 2105-04-13 |  | ACTIVE DEFECTS |  | 40
2 | 45 | 2105-04-13 |  | CLOSED DEFECTS |  | 8
3 | NA | 2015-04-10 |  | EXECUTED TEST CASE |  | 298
|  |  |  | UN EXECUTED TEST CASE |  | 498
COMING Week Priorities
Project ID: |  | W10978 |  | Upcoming Task
Total test Cases to Cover: |  | 109 to 450 |  | Project: |  | W10978
Scheduled date: |  | 2015-05-14 |  | Scheduled Task: |  | New feature
Reason for extending: |  | New requirements from Business |  | Date of release: |  | 2015-05-29